## List1
Harmonogram for testing project for KCT Data
Description | Time (hours) | Cumulative time (in hours)
Documentation, preparation for project etc. | 4 | 4
Creating jUnit tests | 8 | 12
Creating Spring boot application with API | 18 | 30
Preparing data for database | 6 | 36
Creating Angular application | 44 | 80
Estimated days | 80